## Schedules
Job | Title | Complete | State | Duration | Start | End | Assigned To
Bartz, Lyndsay 25 - 48025 Cedarcrest Trl | JOB START | FALSE | In Progress | 1 | 2025-01-01 | 2025-01-01
(*)Office Remodel 25 | JOB START | FALSE | In Progress | 1 | 2025-01-01 | 2025-01-01
Warranty Work | Korri Warranty Work, Champlin | TRUE | Done | 1 | 2025-02-27 | 2025-02-27 | Keith Via
(P) 10582 Juneau Ln N 25 RAILING | JOB START | FALSE | In Progress | 1 | 2025-03-04 | 2025-03-04
Warranty Work | Pulte 10582 Juneau Lane N | TRUE | Done | 1 | 2025-03-04 | 2025-03-04 | Keith Via
Warranty Work | Scholl Warranty Work, Minnetonka (no charge) | TRUE | Done | 1 | 2025-03-06 | 2025-03-06 | Keith Via
Warranty Work | Caci Warranty Work, Corcoran | TRUE | Done | 1 | 2025-03-11 | 2025-03-11 | Keith Via
Warranty Work | May/Youmans Warranty Work, Corcoran | TRUE | Done | 1 | 2025-03-11 | 2025-03-11 | Keith Via
Warranty Work | Halloran Warranty Work, Otsego (no charge) | TRUE | Done | 1 | 2025-03-13 | 2025-03-13 | Keith Via
Warranty Work | Nemetz Warranty Work, Maple Grove | TRUE | Done | 1 | 2025-03-18 | 2025-03-18 | Keith Via
Warranty Work | Turgeon-Schramm Warranty Work, Watertown | TRUE | Done | 1 | 2025-03-25 | 2025-03-25 | Keith Via
Warranty Work | Bohlman Warranty Work, Plymouth (no charge) | TRUE | Done | 1 | 2025-03-27 09:00 | 2025-03-27 | Keith Via
Warranty Work | Crocker Warranty Work, Chanhassen | TRUE | Done | 1 | 2025-04-01 | 2025-04-01 | Keith Via
Warranty Work | Drop off Trailer & Michael's Truck | TRUE | Done | 1 | 2025-04-02 09:00 | 2025-04-02 11:00 | Keith Via, Michael Johnson
Warranty Work | Deck markings at Jeffrey Wall job - Corcoran | TRUE | Done | 1 | 2025-04-03 | 2025-04-03 | Keith Via
TIME OFF - JEREMY | Jeremy Time Off | FALSE | In Progress | 10 | 2025-04-07 | 2025-04-18 | Johnson Family Construction
Warranty Work | Scholl Warranty Work, Minnetonka (no charge) | TRUE | Done | 1 | 2025-04-08 | 2025-04-08 | Keith Via
Warranty Work | (P) Bettmann Warranty Work, Corcoran | TRUE | Done | 1 | 2025-04-10 | 2025-04-10 | Keith Via
Warranty Work | Bolduc Warranty Work, St. Louis Park (no charge) | TRUE | Done | 1 | 2025-04-15 | 2025-04-15 | Keith Via
Warranty Work | Kaul Warranty Work, Corcoran (no charge) | TRUE | Done | 1 | 2025-04-16 | 2025-04-16 | Keith Via
Warranty Work | Assess Broschofsky Deck, Plymouth (no charge) | TRUE | Done | 1 | 2025-04-17 | 2025-04-17 | Keith Via
Warranty Work | Nelson Warranty Work, Maple Grove (no charge) | FALSE | In Progress | 1 | 2025-04-22 | 2025-04-22 | Keith Via
Warranty Work | Chronquist Warranty Assessment, Corcoran | TRUE | Done | 1 | 2025-04-24 09:00 | 2025-04-24 11:00 | Keith Via
Warranty Work | Bann Warranty Work, Eden Prairie (no charge) | TRUE | Done | 1 | 2025-04-28 | 2025-04-28 | Keith Via
Dischinger, Tony 25 | JOB START | FALSE | In Progress | 1 | 2025-04-28 | 2025-04-28
Warranty Work | Logan Warranty Work, St. Michael (no charge) | TRUE | Done | 1 | 2025-04-29 | 2025-04-29 | Keith Via
Warranty Work | Bachmans - Walcker Warranty Work, Mpls (no charge) | TRUE | Done | 1 | 2025-05-01 | 2025-05-01 | Keith Via
Warranty Work | Hollerman Warranty Work, Orono | TRUE | Done | 1 | 2025-05-06 | 2025-05-06 | Keith Via
Warranty Work | Travis Warranty Work, Champlin (no charge) | TRUE | Done | 1 | 2025-05-08 | 2025-05-08 | Keith Via
Swallow, Christina 25 REPAIRS | JOB START | FALSE | In Progress | 1 | 2025-05-13 | 2025-05-13
Warranty Work | Nemetz Warranty Work, Maple Grove (no charge) | TRUE | Done | 1 | 2025-05-15 | 2025-05-15 | Keith Via
Burth, Andy 25 GATE | JOB START | FALSE | In Progress | 1 | 2025-05-19 | 2025-05-19
Warranty Work | Keith - SEE JOB | FALSE | In Progress | 1 | 2025-05-20 | 2025-05-20
Warranty Work | Longman Warranty Work, Plymouth | TRUE | Done | 1 | 2025-05-22 | 2025-05-22 | Keith Via
Warranty Work | Youmans Warranty Work, Corcoran (no charge) | TRUE | Done | 1 | 2025-05-22 09:00 | 2025-05-22 | Keith Via
Warranty Work | Swallow T&M, Shoreview (BILLABLE) | TRUE | Done | 1 | 2025-05-23 | 2025-05-23 | Keith Via
Warranty Work | Jenson Warranty Work, Otsego (no charge) | TRUE | Done | 1 | 2025-05-27 09:00 | 2025-05-27 | Keith Via
Warranty Work | Schandelmeier Warranty Work, Prior Lake | TRUE | Done | 1 | 2025-05-28 | 2025-05-28 | Keith Via
Hennesen Warranty Work | Billy - Corcoran | FALSE | In Progress | 1 | 2025-05-29 | 2025-05-29
Warranty Work | Haque Warranty Work, Eagan | TRUE | Done | 1 | 2025-05-29 | 2025-05-29 | Keith Via
Warranty Work | Miller Billable Repair, Minnepolis (BILL) | FALSE | In Progress | 1 | 2025-05-29 | 2025-05-29 | Keith Via
Sparks, Laura 25 | Bill-Plymouth | FALSE | In Progress | 4 | 2025-05-30 | 2025-06-04 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Warranty Work | Kademani, Rupam Warranty Work, Medina | TRUE | Done | 1 | 2025-05-30 | 2025-05-30 | Keith Via
Warranty Work | Kademani Warranty Work, Medina | TRUE | Done | 5 | 2025-06-03 | 2025-06-09 | Keith Via
Warranty Work | Kaul Warranty Work, Corcoran (no charge) | TRUE | Done | 1 | 2025-06-03 | 2025-06-03 | Keith Via
Warranty Work | Brott Warranty Work, St. Michael (no charge) | TRUE | Done | 1 | 2025-06-05 | 2025-06-05 | Keith Via
Geisen, Steve & Mary 25 HIDEAWAY | Geisen - Dayton (Install Hideaway Posts) | FALSE | In Progress | 1 | 2025-06-10 | 2025-06-10 | Keith Via
Warranty Work | (P) Bettmann Warranty Work, Corcoran | TRUE | Done | 1 | 2025-06-10 09:00 | 2025-06-10 | Keith Via
Warranty Work | Kademani Warranty Work | TRUE | Done | 1 | 2025-06-11 | 2025-06-11 | Keith Via
Warranty Work | Descamps Warranty Work, Corcoran | TRUE | Done | 1 | 2025-06-12 | 2025-06-12 | Keith Via
Warranty Work | Grunewald Warranty Work, Rogers | TRUE | Done | 1 | 2025-06-12 | 2025-06-12 | Keith Via
Warranty Work | Miller Billable Repair, Minnepolis (BILL) | TRUE | Done | 1 | 2025-06-13 | 2025-06-13 | Keith Via
Warranty Work | Logan Warranty Work, St. Michael | TRUE | Done | 1 | 2025-06-16 | 2025-06-16 | Keith Via
Warranty Work | Kamalapuram (prev Alves) Warranty Work, Corcoran | TRUE | Done | 1 | 2025-06-17 | 2025-06-17 | Keith Via
Warranty Work | Agarwala Warranty Work, Plymouth | TRUE | Done | 1 | 2025-06-18 | 2025-06-18 | Keith Via
Warranty Work | Berman Warranty Work, Wayzata | TRUE | Done | 1 | 2025-06-19 | 2025-06-19 | Keith Via
Warranty Work | Ingraham Assessment, Minnetonka | TRUE | Done | 1 | 2025-06-19 | 2025-06-19 | Keith Via
Warranty Work | Ingraham Warranty Work, Minnetonka | TRUE | Done | 1 | 2025-06-19 | 2025-06-19 | Keith Via
Warranty Work | Kamalapuram Warranty Work, Corcoran | TRUE | Done | 2 | 2025-06-24 | 2025-06-25 | Keith Via
Warranty Work | Vining Warranty Work, Hanover | TRUE | Done | 1 | 2025-06-24 | 2025-06-24 | Keith Via
Warranty Work | Stewart Warranty Work, Dayton | TRUE | Done | 1 | 2025-06-24 09:00 | 2025-06-24 | Keith Via
Mlodzik, Travis 25 | Bill-Lakeville | FALSE | In Progress | 4 | 2025-06-26 | 2025-07-01 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Warranty Work | West RainEscape Repair, Maple Grove | TRUE | Done | 1 | 2025-06-26 | 2025-06-26 | Keith Via
Warranty Work | Agarwala Warranty Work, Plymouth | TRUE | Done | 1 | 2025-07-01 | 2025-07-01 | Keith Via
Schrader, Kari 25 | Ben-Maple Grove | FALSE | In Progress | 7 | 2025-07-01 | 2025-07-09 | Benjamin Dols Subcontracting
Warranty Work | Pumarlo RainEscape, Corcoran | TRUE | Done | 1 | 2025-07-01 | 2025-07-01 | Keith Via
McNamara, Amy & Devon 25 | Bill- St. Michael | FALSE | In Progress | 12 | 2025-07-02 | 2025-07-17 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Warranty Work | Phillips Warranty Work, Orono | TRUE | Done | 1 | 2025-07-03 | 2025-07-03 | Keith Via
Warranty Work | Snede Warranty Work, Excelsior | TRUE | Done | 1 | 2025-07-03 | 2025-07-03 | Keith Via
(P) Beck, Richard & Mary 25 | Ben-Ledger Corcoran | FALSE | In Progress | 1 | 2025-07-07 | 2025-07-07 | Benjamin Dols Subcontracting
Warranty Work | Ingraham Warranty Work, Mtka | TRUE | Done | 1 | 2025-07-07 | 2025-07-07 | Keith Via
Dischinger, Tony 25 | Keith - Pull Down Soffit @ Dischinger | FALSE | In Progress | 1 | 2025-07-07 | 2025-07-07 | Keith Via
Wang, Xuan 25 | Jeremy-Plymouth | FALSE | In Progress | 4 | 2025-07-08 | 2025-07-11 | Johnson Family Construction
Warranty Work | Kademani Warranty Work, Corcoran | TRUE | Done | 1 | 2025-07-08 | 2025-07-08 | Keith Via
Skagerberg, Joel & Karen 25 | Ben-Maple Grove | FALSE | In Progress | 10 | 2025-07-10 | 2025-07-23 | Benjamin Dols Subcontracting
Walker, Tom 25 REPAIRS BILLABLE | JOB START | FALSE | In Progress | 1 | 2025-07-10 | 2025-07-10
Warranty Work | Walker BILLABLE Repair, Mound | TRUE | Done | 1 | 2025-07-10 | 2025-07-10 | Keith Via
Frederick, Mia & Connor 25 | DLC-Victoria | FALSE | In Progress | 2 | 2025-07-11 | 2025-07-14 | DLK De La Cruz Construction
Johnson, Mary Beth 25 | Jeremy-Mendota Heights | FALSE | In Progress | 8 | 2025-07-14 | 2025-07-23 | Johnson Family Construction
Wang, Xuan 25 | Wang Final Inspection and HMO Walk Through | FALSE | In Progress | 1 | 2025-07-14 11:00 | 2025-07-14 12:00 | Kyle Becklin
Garvis, Rhonda 25 REPAIRS | Keith-Garvis Repairs | FALSE | In Progress | 1 | 2025-07-15 | 2025-07-15
Warranty Work | Garvis BILLABLE Repair, Plymouth | TRUE | Done | 1 | 2025-07-15 09:00 | 2025-07-15 | Keith Via
Warranty Work | Dischinger Job | TRUE | Done | 1 | 2025-07-16 | 2025-07-16 | Keith Via
Warranty Work | Davies BILLABLE Repair, Maple Grove | TRUE | Done | 1 | 2025-07-17 | 2025-07-17 | Keith Via
Warranty Work | Descamps Warranty Work, Corcoran | TRUE | Done | 1 | 2025-07-17 | 2025-07-17 | Keith Via
Warranty Work | Horn Warranty Work, Corcoran | TRUE | Done | 1 | 2025-07-17 | 2025-07-17 | Keith Via
Davies, Jim REPAIRS BILLABLE | JOB START | TRUE | Done | 1 | 2025-07-17 | 2025-07-17 | Keith Via
Gerritsen, Jim & Kathy 25 ESCROW | Bill-Corcoran | FALSE | In Progress | 4 | 2025-07-18 | 2025-07-23 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Warranty Work | Bettmann Warranty Work, Corcoran | TRUE | Done | 1 | 2025-07-21 | 2025-07-21 | Keith Via
(P) Wallin, Bob & Patti 25 | Ledger Corcoran | FALSE | In Progress | 1 | 2025-07-21 | 2025-07-21 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Hrdlichka, Scott & Bonnie 25 REDECK STEPS | Keith-Hrdlichka REDECK STEPS | TRUE | Done | 1 | 2025-07-22 | 2025-07-22 | Keith Via
Johnson, Kathy 25 STAIRCASE | DLC-Dayton | FALSE | In Progress | 2 | 2025-07-23 | 2025-07-24 | DLK De La Cruz Construction
Warranty Work | Garcia Light Warranty, Farmington | TRUE | Done | 1 | 2025-07-23 | 2025-07-23 | Keith Via
Sabart, Darcee & Doug 25 | Jeremy-New Hope | FALSE | In Progress | 5 | 2025-07-23 | 2025-07-29 | Johnson Family Construction
Warranty Work | Johnson Assessment, Ramsey | TRUE | Done | 1 | 2025-07-24 | 2025-07-24 | Keith Via
Johnson, Mary Beth 25 | Johnson Final Inspection | FALSE | In Progress | 1 | 2025-07-25 11:30 | 2025-07-25 12:30 | Kyle Becklin
Gerritsen, Jim & Kathy 25 ESCROW | Gerritsen Final Inspection | FALSE | In Progress | 1 | 2025-07-28 11:00 | 2025-07-28 12:00 | Kyle Becklin
Thompson, Bryan BEAM REPLACEMENT | Bill-Maple Grove | FALSE | In Progress | 2 | 2025-07-29 | 2025-07-30 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Polen, Doug & Ellen 25 | Bill-Maple Plain | FALSE | In Progress | 3 | 2025-07-31 | 2025-08-04 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Burtzel, Aaron 25 GATE | Keith-Burtzel GATE | TRUE | Done | 1 | 2025-07-31 | 2025-07-31 | Keith Via
Johnson, Kathy 25 STAIRCASE | Johnson Final Inspection & HMO Walk Through | FALSE | In Progress | 1 | 2025-07-31 13:00 | 2025-07-31 14:00 | Kyle Becklin
Sabart, Darcee & Doug 25 | Sabart Final Inspection & HMO Walk Through | FALSE | In Progress | 1 | 2025-08-01 10:30 | 2025-08-01 11:30 | Kyle Becklin
Riedel, Linda 25 | Chad-Eden Prairie | FALSE | In Progress | 10 | 2025-08-04 | 2025-08-15 | Leading Edge Construction
Macnamara, Rob & Laura 25 | Bill- Medina | FALSE | In Progress | 4 | 2025-08-05 | 2025-08-08 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Johnson, Mike 25 WARRANTY | Keith-Ramsey | TRUE | Done | 2 | 2025-08-05 | 2025-08-06 | Keith Via
Lucke, Colleen 25 | Ben-Edina | FALSE | In Progress | 7 | 2025-08-06 | 2025-08-14 | Benjamin Dols Subcontracting
Warranty Work | Blake Repair, Rogers | TRUE | Done | 1 | 2025-08-07 | 2025-08-07 | Keith Via
Skagerberg, Joel & Karen 25 | Skagerberg HMO Walk Through | FALSE | In Progress | 1 | 2025-08-07 09:00 | 2025-08-07 10:00 | Kyle Becklin
Warranty Work | Hunt Light Assessment, North Oaks | TRUE | Done | 1 | 2025-08-08 | 2025-08-08 | Keith Via
Skagerberg, Joel & Karen 25 | Skagerberg Final Inspection | FALSE | In Progress | 1 | 2025-08-11 09:00 | 2025-08-11 10:00 | Kyle Becklin
Warranty Work | Bartz Lattice Install | TRUE | Done | 1 | 2025-08-12 | 2025-08-12 | Keith Via
Ingraham, Dave 25 | DLC-Minnetonka | FALSE | In Progress | 4 | 2025-08-12 | 2025-08-15 | DLK De La Cruz Construction
Sparks, Laura 25 | Sparks Final Inspection & HMO Walk Through | FALSE | In Progress | 1 | 2025-08-12 13:30 | 2025-08-12 14:30 | Kyle Becklin
Polen, Doug & Ellen 25 | Bill-Maple Plain | FALSE | In Progress | 15 | 2025-08-13 | 2025-09-02 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Warranty Work | Guler Assessment, Maple Grove | TRUE | Done | 1 | 2025-08-13 | 2025-08-13 | Keith Via
(P) Van Vleet, Blake & Sovannara Por 25 | Ledger Farmington | FALSE | In Progress | 1 | 2025-08-13 | 2025-08-13 | Leading Edge Construction
Warranty Work | Frodl Staircase Assessment, Medina | TRUE | Done | 1 | 2025-08-14 | 2025-08-14 | Keith Via
Macnamara, Rob & Laura 25 | Macnamara Final Inspection | FALSE | In Progress | 1 | 2025-08-14 13:30 | 2025-08-14 14:30 | Kyle Becklin
Skavnak, Jen 25 | Chad-Edina | FALSE | In Progress | 13 | 2025-08-18 | 2025-09-03 | Leading Edge Construction
Warranty Work | Bettinger REPAIRS | TRUE | Done | 1 | 2025-08-21 | 2025-08-21 | Keith Via
Warranty Work | Molenaar Light Assessment, Maple Grove | TRUE | Done | 1 | 2025-08-21 | 2025-08-21 | Keith Via
Warranty Work | (P) Nedved Warranty Work, Rosemount | TRUE | Done | 1 | 2025-08-22 08:00 | 2025-08-22 12:00 | Keith Via
Macnamara, Rob & Laura 25 | Macnamara Final Walk Through | FALSE | In Progress | 1 | 2025-08-22 08:00 | 2025-08-22 09:00 | Kyle Becklin
Lucke, Colleen 25 | Ben-Edina | FALSE | In Progress | 4 | 2025-08-25 | 2025-08-28 | Benjamin Dols Subcontracting
Rockwell, Dan 25 | Igor-Eagan | FALSE | In Progress | 3 | 2025-08-25 | 2025-08-27 | Tur Construction
Bachman, Jim 25 REPAIRS | Keith-Blaine | TRUE | Done | 2 | 2025-08-26 09:00 | 2025-08-27 | Keith Via
Russ, Oral 25 | Jeremy-Ramsey | FALSE | In Progress | 6 | 2025-08-27 | 2025-09-03 | Johnson Family Construction
Hoffman, Wendell 25 | Keith-Woodbury INSTALL PANELS | TRUE | Done | 1 | 2025-08-27 | 2025-08-27 | Keith Via
Rystad, Betty 25 | Ben-Edina | FALSE | In Progress | 2 | 2025-09-02 | 2025-09-03 | Benjamin Dols Subcontracting
Jacobsen, Lani 25 | Ben-Edina | FALSE | In Progress | 1 | 2025-09-03 | 2025-09-03 | Benjamin Dols Subcontracting
Talmage, Ross 25 PANELS | Keith-Plymouth | TRUE | Done | 1 | 2025-09-03 | 2025-09-03 | Keith Via
Warranty Work | Teske Warranty Work, Greenfield | TRUE | Done | 1 | 2025-09-03 | 2025-09-03 | Keith Via
Lucke, Colleen 25 | Lucke Final Inspection | FALSE | In Progress | 1 | 2025-09-03 13:00 | 2025-09-03 14:00 | Kyle Becklin
Rockwell, Dan 25 | Rockwell Final Inspection | FALSE | In Progress | 1 | 2025-09-03 13:30 | 2025-09-03 14:30 | Kyle Becklin
(P) Beck, Richard & Mary 25 | Ben | FALSE | In Progress | 3 | 2025-09-04 | 2025-09-08 | Benjamin Dols Subcontracting
(P) Raygor, Elizabeth 25 | Bill-Ledger | FALSE | In Progress | 1 | 2025-09-04 | 2025-09-04 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Anderson, Josh 25 | Bill-Plymouth | FALSE | In Progress | 7 | 2025-09-04 | 2025-09-12 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Roselius, Kate 25 | Chad-Minnetonka | FALSE | In Progress | 7 | 2025-09-04 | 2025-09-12 | Leading Edge Construction
Zappa, Ron & Sue 25 RAILING #2 | Keith-Corcoran | TRUE | Done | 1 | 2025-09-04 | 2025-09-04 | Keith Via
Griffith, Desiree 25 | DLC-Corcoran | FALSE | In Progress | 5 | 2025-09-05 | 2025-09-11 | DLK De La Cruz Construction
Russ, Oral 25 | Russ Final Inspection | FALSE | In Progress | 1 | 2025-09-05 11:30 | 2025-09-05 12:00 | Kyle Becklin
Russ, Oral 25 | Russ HMO Walk Through | FALSE | In Progress | 1 | 2025-09-05 12:00 | 2025-09-05 13:00 | Kyle Becklin
(P) Beck, Richard & Mary 25 | Beck Final Inspection | FALSE | In Progress | 1 | 2025-09-08 | 2025-09-08 | Kyle Becklin
Bartel, Garret 25 | Jeremy-Hamel | FALSE | In Progress | 4 | 2025-09-08 | 2025-09-11 | Johnson Family Construction
Brua, Kyle & Lisa 25 | Ben-Corcoran | FALSE | In Progress | 7 | 2025-09-09 | 2025-09-17 | Benjamin Dols Subcontracting
Jacobsen, Lani 25 | Jacobsen Final Inspection & HMO Walk Through | FALSE | In Progress | 1 | 2025-09-10 13:00 | 2025-09-10 14:00 | Kyle Becklin
Rystad, Betty 25 | Rystad Final Inspection | FALSE | In Progress | 1 | 2025-09-10 13:00 | 2025-09-10 14:00 | Kyle Becklin
Warranty Work | Campbell Warranty Work, Corcoran | TRUE | Done | 1 | 2025-09-11 | 2025-09-11 | Keith Via
Warranty Work | Teske Warranty Work | FALSE | In Progress | 1 | 2025-09-11 | 2025-09-11 | Keith Via
Polen, Doug & Ellen 25 | Polen Final Inspection | FALSE | In Progress | 1 | 2025-09-11 13:00 | 2025-09-11 14:00 | Kyle Becklin
Smith, Jack & Taryn 25 | Bill-Corcoran | FALSE | In Progress | 5 | 2025-09-15 | 2025-09-19 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Skavnak, Jen 25 | Chad-Edina | FALSE | In Progress | 2 | 2025-09-15 | 2025-09-16 | Leading Edge Construction
Heinen, Kori 25 | Jeremy-Champlin | FALSE | In Progress | 8 | 2025-09-15 | 2025-09-24 | Johnson Family Construction
Anderson, Josh 25 | Anderson Final Inspection | FALSE | In Progress | 1 | 2025-09-15 10:30 | 2025-09-15 11:30 | Kyle Becklin
LaChance, John 25 | Keith-Corcoran | TRUE | Done | 1 | 2025-09-16 | 2025-09-16 | Keith Via
McCole, Brian & Andrea 25 POST WRAPS & SOFFIT | Chad-Corcoran | FALSE | In Progress | 2 | 2025-09-17 | 2025-09-18 | Leading Edge Construction
Anderson, Josh 25 | Anderson HMO Walk Through | FALSE | In Progress | 1 | 2025-09-18 | 2025-09-18 | Kyle Becklin
Polen, Doug & Ellen 25 | Polen HMO Walk Through | FALSE | In Progress | 1 | 2025-09-18 | 2025-09-18 | Kyle Becklin
(P) 16290 Comstock Ln Dayton 25 | Ben-Ledger | FALSE | In Progress | 1 | 2025-09-19 | 2025-09-19 | Benjamin Dols Subcontracting
(P) Van Vleet, Blake & Sovannara Por 25 | Chad-Farmington | FALSE | In Progress | 5 | 2025-09-19 | 2025-09-25 | Leading Edge Construction
Froehle, Paul 25 ESCROW | Ben-Corcoran | FALSE | In Progress | 8 | 2025-09-22 | 2025-10-01 | Benjamin Dols Subcontracting
Boyington, Bryan 25 | Bill-Corcoran | FALSE | In Progress | 5 | 2025-09-22 | 2025-09-26 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
(P) Wallin, Bob & Patti 25 | Bill-Corcoran | FALSE | In Progress | 3 | 2025-09-22 | 2025-09-24 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Patel, Neel 25 | Jeremy-Plymouth | FALSE | In Progress | 10 | 2025-09-25 | 2025-10-08 | Johnson Family Construction
Kooken, Kelly & Alden 25 | Bill-Maple Grove | FALSE | In Progress | 3 | 2025-09-29 | 2025-10-01 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Schilling, Kevin & Andrea 25 | Chad-Bloomington | FALSE | In Progress | 9 | 2025-09-29 | 2025-10-09 | Leading Edge Construction
Manley, Joy 25 | DLC-Plymouth | FALSE | In Progress | 2 | 2025-09-29 | 2025-09-30 | DLK De La Cruz Construction
Byrne, Tim 25 | Bill-Minnetonka | FALSE | In Progress | 5 | 2025-10-01 | 2025-10-07 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Scholl, Aaron BEAM REPLACEMENT | Ben | FALSE | In Progress | 1 | 2025-10-02 | 2025-10-02 | Benjamin Dols Subcontracting
Erickson, Tina & Steve 25 | Bill-Plymouth | FALSE | In Progress | 6 | 2025-10-08 | 2025-10-15 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
(P) 10464 Grospoint Ave Cottage Grove 25 | Jeremy-Cottage Grove | FALSE | In Progress | 3 | 2025-10-09 | 2025-10-13 | Johnson Family Construction
(P) 16290 Comstock Ln Dayton 25 | Ben-Dayton | FALSE | In Progress | 3 | 2025-10-13 | 2025-10-15 | Benjamin Dols Subcontracting
Mergenthal, Brady 25 | Chad-Prior Lake | FALSE | In Progress | 4 | 2025-10-13 | 2025-10-16 | Leading Edge Construction
(P) Raygor, Elizabeth 25 | Bill-Corcoran | FALSE | In Progress | 4 | 2025-10-16 | 2025-10-21 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Parmley, Lucas 25 | Ben-Dayton | FALSE | In Progress | 9 | 2025-10-20 | 2025-10-30 | Benjamin Dols Subcontracting
Dinneen, Matt 25 | Chad-Farmington | FALSE | In Progress | 5 | 2025-10-20 | 2025-10-24 | Leading Edge Construction
Groppoli, Laura & Mark 25 | Bill-Edina | FALSE | In Progress | 7 | 2025-10-21 | 2025-10-29 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Dishop, Josh & Lee 25 | Ben-Carver | FALSE | In Progress | 10 | 2025-10-27 | 2025-11-07 | Benjamin Dols Subcontracting
Wright, Tom 25 | Bill Loretto | FALSE | In Progress | 9 | 2025-10-27 | 2025-11-06 | William Ritchie Subcontracting - Billy, William Ritchie Subcontracting - Syd
Kammer, John 25 | Chad-Savage | FALSE | In Progress | 2 | 2025-10-27 | 2025-10-28 | Leading Edge Construction
Neary, Bill 25 | JOB START | FALSE | In Progress | 1 | 2025-10-27 | 2025-10-27
Haven, Darlene 25 | JOB START | FALSE | In Progress | 1 | 2025-11-03 | 2025-11-03